## Sheet1
ENTERPRISE ARCHITECTURE TEAM TASK TRACKER
No | Assignee | Pno | Project Name | Project Desctrption | Task name | Design Status | Dev Status | SIT Status | Progress Notes updates | Priority | BA/PM | Start Date | Due Date | Dependencies | Comments
2 | Amon Sabul |  | TSC loan topup bypass | Bypass the 30 days initial requirement before TSC members are given a loan/Topup | Solution design | Completed |  |  | Solution Design - Done | high | Erastus Kinuthia
|  |  | Tranzmit MTO cooperative bank integration | Onboarding Tranzmit as a new MTO for open banking | Solution Design | Completed |  |  |  | high | Leslie Madegwa
|  | 2 | RTGS API onboarding on open banking | Onboarding RTGS as a payment method on open banking | Solution design | Completed |  |  | solution design ongoing | Medium | Dennis Nyahanga
|  | 3 | card track system | the goal is to develop a card track system which tracks the movement of cards from the vendor to the customer | Solution design - 22-8-2025 | Completed |  |  | done | High | Kyalo Mule
|  | 1 | IPSL pay to merchant incoming | This is to enable offline capabilities for E-citizen on POS | Solution design | Completed |  |  | solution design done and shared with business | high
|  | 2 | Request for Quote (RFQ) (TMS) | duplication checks from RFQ to TMS(acumen) | service enhancments | Completed |  |  | changes on the services and fixing bugs ongoing | high
|  | 6 | Open banking API optimization | This involves optimizing the current flow on open banking platform to minimize jitters and enhance faster TAT for Transactions | reviews and redesign - to review 22-8 revert on Tuesday | Completed |  |  | review on the existing services is ongoing | high | Elizabeth Njau
|  | 7 | IPF bancassurance - finacle - integration | The goal is to automate reconciliation to close to real time between finacle, bancassurance and BPMS | Solution design | Completed |  |  | solution design ongoing | medium
|  | 3 | Salary Processing Enhancement for south sudan | South Sudan needs the current Salary Processing System enhanced to support up to 20,000 records, an increase from the current capacity of 400, attached is the CR. | Solution design | Completed |  |  |  | medium
|  | 4 | Tranzmit MTO (solutioning and support) | The goal is to onboard Tranzmit as a MTO | Solution design and support | Completed |  |  |  | medium
|  | 5 | Bancassurance IPF auto receipting | Automate the validation/advise process | Solution design and support | Completed
|  | 7 | Pay angel Open banking integration | onboard Payangel to the MTO/Open banking platform | solution design | Completed
|  | 10 | API based access to prequalified MSME customer limits | this is to retrieve limits for prequalified MSME customers | Solution design | Completed |  |  | solution design ongoing | medium
|  | 11 | STK Push Mpesa redesign | this was to change the token requests by the STK service on C2B | Solution design | Completed |  |  |  | high
|  | 12 | MICR cheque book splitting based on vendors | this change was to enable cheque printing to be done by more than one vendor based on regions | Solution design | Completed |  |  |  | high
|  | 13 | SOA update COLAS scheme code | this was to update the validation service to allow specified scheme codes | review and enhancments | Completed |  |  |  | high
|  | 14 | Offline - POS - Ecitizen | This is to enable offline capabilities for E-citizen on POS | Solution design | Completed |  |  |  | medium
|  | 16 | SMS gateway metering | the goal was to have a portal that can onboard and manage new patners who can use the cooperative banks SMS gatewayAPI | Solution design | Completed |  |  | review and support is still ongoing | high
|  |  | Treasury management System RFQ | design the Request for quotation feature on treasury management system to be used by channels e.g RBX/CBX/Branch | solution design | Completed |  |  | solution design is done | high | Samuel Thuku
|  |  | Lipa na Mpesa (LNM) tariff configuration - safaricom paybill bouquets | Enhancement is aimed at improving onboarding process of merchants using paybill services by enabling branch users to select specific paybill tariffs customer bouquets | solution design done | Completed |  |  | solution design is done | high
|  | 4 | digital receipts | implementing digital receipts on ATMs and POS | solution design enhancement ongoing to capture the brd changes | Completed |  |  | ongoing | high | Vincent Buluma
|  | 5 | Adding agent number validation for mpesa float purchase on CDMs | Validation of store number and agent number for each M-pesa Float purchase on CDM machines. Where the store number and agent number is a matching record, the CDM will request amount entry and cash be placed on the cash tray and confirmed. The transaction will be continued, and float credited. | solution design to be done | Completed |  |  | ongoing | high | Paul Mboroki
|  | 6 | Tranzmit MTO cooperative bank integration | Onboarding Tranzmit as the new MTO on teller portal | Solution Design | Completed |  |  | done | high | Leslie Madegwa
|  | 8 | Micr cheque printing split to accomodate other vendors in cheque printing | design to offload tasks for cheque printing from a single vendor to other vendors | Solution design | Completed
|  | 9 | Ammend retail customer service to accomodate other parameters | enhance the service to accomodate classification, document update, and also employee details | solution design | Completed
3 | Samuel Mburu | 1 | self onboarding and self self service on coop till app | 1. Onboarding of new merchant (Has a Co-opbank A/c WITH NO Co-op Till) | Solution design | Completed | In-Progress |  | Reviewing the CR and working on the solution design thereafter | High | Elias Ronoh
2.Onboarding existing merchant.
3. Introducing Self service capabilities like password reset and unlock user.
|  | 2 | Shortened JJ Account Onboarding-New to Bank and Existing | Reduce the account opening fields and screens | Solution design | Completed | In-Progress |  | Backend and Frontend development on-going | High | Joseck Kariuki
|  | 6 | Visa Subscription management | Allow users manage thier cards on Omni | Development | Completed | In-Progress
|  | 8 | Enhance eloans to allow customer request of Letter of offer. This will be handled by reports engine, decoupling the logic from the channels | Allow customer to request letter of offer | Solution design | Completed | In-Progress
|  | 9 | Deposit Secured Ecredit | Allow E-flexi customers with collateral secure thier loan | Solution design | Completed | Pending
|  | 8 | Yea and Mco-opCash 5.1 | 3. Introducing Self service capabilities like password reset and unlock user. | Solution design | Completed |  |  | On-going | High | Robert Kairu
4 | Everlyne Mosomi | 1 | QMS intergration to CRM | Develop and maintain clear documentation of all architectural components to guide future development, integration, and scalability of the platform. | Support development CR and Solution document review | Completed | In-Progress |  | Development on going from QMS team |  | Lesile Muthoka
|  | 1 | Statement engine South Sudan | an engine to generate account statement for cooperative bank south Sudan instead of using the core banking ( Finnacle) system which is currently the case | Solution Design | Completed | In-Progress |  | Completed updating the solution design | Medium | Paul Mburoki
|  | 3 | Two way Sms | To facilitate text messaging for Airtel and telcom subscribers through the SMS short code 16111 and customers to be able to respond to the message. | Solution Design | Completed |  |  | UAT testing stage |  | Regina Nzomo
|  | 4 | Statement engine CoopBank kenya enhancement | statement generation process on the engine is generally seamless, several issues have been observed when handling accounts with multiple signatories, agents, and internal account types | Solution Design | Completed |  |  | ;pz | high | Rosemary Nduta
|  |  | Cisco Unified Communications Manager Upgrade Project | The Cisco Unified Communications Manager (CUCM) Upgrade Project aims to modernize Cooperative Bank’s voice communication infrastructure by upgrading the system from version 9.1.2 to version 14 . The current system is running on End-of-Life (EOL) and End-of-Support (EOS) software and hardware, posing risks in security, compliance, availability, and scalability . | SIT approval Pre-CAB approval | Completed |  |  | SIT Approval Done-4/30/25 Next step Pre-CAB approval-Done Phase 1- Done 5/12/25 Phase 2 Sudan-TBA | High | James Ouko
|  | 2 | CO-OPBANK AND PAPSS INTEGRATION DESIGN | The Pan African Payment and Settlement System (PAPSS) is a platform that offers an alternative option for doing the same. However, PAPSS is limited to Banks within Africa Continent, Supports the African Currencies and is near instant Payment | Solution Design | Completed | In-Progress |  | Service testing with the vendor | Medium | George Njogo
|  | 3 | Enhancement of Credit administration dataclass in EDMS | enhancing the data fetching capabilities within the Credit Administration dataclass of the Enterprise Document Management System (EDMS). The goal is to enable indexing and retrieval of documents using the CIF ID (Customer Number), in addition to the current requirement of the 14-digit | Solution Design | Completed | Completed | In-Progress | Support Development | Medium | Amina Saidi
account number.
|  | 5 | Review of Personal Loan Pricing Model for TSC and Kenya Prisons Schemes solution | This document outlines a comprehensive solution to reconfigure the core banking system (Finacle) and associated processes mostly on loan tenor increase and charges repayment | Solution design | Completed | Completed | Completed | Completed the solution docement | High | Leslie Mutoka | 18/09/2025 | 2025-01-10
5 | Dan Ronoh | 1 | Cisco ISE Posture and DC Switches | This project outlines a 3-year roadmap (2024–2027) to modernize the Bank’s Cisco Identity Services Engine (ISE) deployment for enhanced Network Access Control (NAC). The initiative focuses on upgrading from ISE version 3.0 to 3.2+ to address end-of-life risks, adopt advanced features like posture enforcement, threat-centric NAC (TC-NAC), and integrate with Cisco DNA Center for SD-Access. It also involves resizing licenses to include 7,000 Premier licenses for comprehensive NAC capabilities and 5,000 Essential licenses for non-interactive devices, ensuring scalability for projected growth (11,979 endpoints by 2027). Additionally, the plan addresses high availability and disaster recovery risks by redeploying nodes to eliminate single points of failure in the DR site, while aligning with Cisco Catalyst 9300+ switches for future SD-Access readiness. The outcome will be a secure, scalable, and resilient NAC architecture that supports compliance, automation, and modern network demands. | Reference calls Few Ref Calls Pending -Done Vendor Negotiation-Done Financials-done | Completed |  |  | Done | medium | William Warui
|  | 3 | BMPS Upgrade | BPMS Upgrade Project aims to modernize the bank’s ProcessMaker system (v3.5.8 → v3.8.x) to resolve compatibility issues with MySQL 8.0.34 , enhance security, and enable advanced features like scheduled processes and real-time KPI dashboards. The upgrade ensures alignment with the bank’s enterprise technology roadmap and regulatory compliance, while supporting 1.2 million annual cases . | Roadmap draft-Done Roadmap update -Done Kick-off-6/23/2025 Governace-ongoing | Completed |  |  | ongoing | high | Beatrice Gathoni
|  | 4 | Co-op Pay Digitization | The CoopPay solution digitizes and automates the prepaid card issuance and replacement process for Co-op Bank, addressing revenue leakage, audit gaps, and manual inefficiencies. | Solution Design- User Journey Completed . API alignment-To be done | Completed |  |  | Ongoing | high | Kenna Gachutha
It introduces a public-facing digital application portal (forms.co-opbank.co.ke) and enforces mandatory prepayment before any card is produced.
|  | 5 | Disparities in Finacle/SOA Turnovers vs BI Turnovers | On getAccountTurnoverDetails service, there's a mapping on the lowest balance that needs to be corrected from lowBalCredit to lowBalDebit field. |  | Completed |  |  | Mapping Done Pre-prod testing done Production deployment -awaiting deployment after code freeze started on 25/6/2025 | medium | Geoffrey Mesesi
|  | 6 | Cisco Unified Communications Manager (CUCM) | Modernize the bank’s voice communication infrastructure by upgrading CUCM from v9.1.2 to v14. Addresses EOL systems, enhances security, scalability, and compliance, and enables integration with collaboration tools (Teams, Webex). Ensures high availability, supports future growth, and improves productivity and customer service. | SIT Approval Done-4/30/25 Next step Pre-CAB approval-Done SSD-TBA | Completed |  |  | Done | high | James Ouko
|  | 7 | SMS Gateway | The Metering SMS Gateway Solution is a strategic initiative by Co-op Bank to modernize and expand its existing SMS Gateway infrastructure to support secure, metered, and scalable access for external institutions such as SACCOs, microfinance institutions, fintechs, schools, and other banks. | Roadmap- draft | Completed |  |  | Done | medium
|  | 9 | Hardware DNS and IPAM | The bank is embarking on a strategic infrastructure modernization initiative to replace its current Active Directory-integrated DNS with a dedicated, hardware-based Adaptive DNS and IPAM solution from Infoblox . This transformation aims to address critical limitations in scalability, security, performance, automation, and compliance of the existing DNS architecture. | Roadmap Update -Done Finacials-Done | Completed |  |  | Done | high | William Warui
|  | 10 | DIGITIZATION OF THE HR RECRUITMENT PROCESS | The bank is implementing a modern Recruitment Automation System (RAS) to replace its current manual and Excel-based recruitment process. The goal is to streamline end-to-end hiring operations, improve candidate experience, enhance compliance, and support data-driven decision-making through integrated AI tools and centralized dashboards. | Roadmap initial-Done | Completed |  |  | Ongoing | High | Amina Saidi
7 | David Barmasai | 1 | XDR | Project for acquisition of IT Service management system. The project is currently in the RFP process. | RFP process support and Roadmap Design | In-Progress |  |  | The RFP process is at Finanial Proposal discussions stage. Discussions are ongoing to seek clarifications on licensing models by different vendors | Medium | Paul Mboroki
|  | 2 | NDR | Project for acquisition of a new CRM system. The project is currently in the RFP process | RFP process support and Roadmap Design | In-Progress |  |  | The RFP process is at Finanial Proposal discussions stage. Discussions are ongoing to seek clarifications on licensing models by different vendors | Medium | Vincent Buluma
|  | 3 | CRM | Project for acquisition of Digital Assisstant system. The project is currently in the RFP process | RFP process support and Roadmap Design | In-Progress |  |  | Reference calls to various vendor sites concluded. Preparations ongoing for POC stage | Medium | Brigid Fernandes
|  | 4 | Digital Assistant | Following dynamic Threat Landscape by Cyberattacks, the bank is acquiring Cyber Threat Intelligence system for IT Security to aid in reducing time of threat detection and response and to mitigate data loss arising from cyberattack | Support throught the RFP process | In-Progress |  |  |  | High | Valentine Wangari
|  | 5 | Cyber Threat Intelligence System | The bank is currently running a Cisco Wi-Fi deployment consisting of a 5508-model wireless controller and 34 access points spread across the HQs and the LMC. The wireless access points are Cisco Aironet 3700 and 3600 Series which are also end of support. Additionally, the wireless controllers were initially a cluster of 3; 2 in Co-op Trust DC and 1 in DR, however, 2 of the controllers have since been decommissioned due to irreparable hardware fault and as such the bank is running on a singular controller which is a single point of failure for the entire Wi-Fi network. | Support throught the RFP process | In-Progress |  |  | Project currently at Reference Calls stage | Medium | Valentine Wangari
|  | 6 | Checkpoint SLA Renewal | The Bank has been running a backup solution which is supported by Commvault software and NetApp Storage. The backup solution was implemented in 2020 with 5 years support contract for both hardware and software.With the License Expiration, there is risk of interrupted system operations | Support throught the RFP process | In-Progress |  |  | Project currently at Desktop Evaluation stage | High | Marystella Obulutsa
|  | 7 | Commvault Backup Solution | The bank is currently running a Cisco Wi-Fi deployment consisting of a 5508-model wireless controller and 34 access points spread across the HQs and the LMC. The wireless access points are Cisco Aironet 3700 and 3600 Series which are also end of support. Additionally, the wireless controllers were initially a cluster of 3; 2 in Co-op Trust DC and 1 in DR, however, 2 of the controllers have since been decommissioned due to irreparable hardware fault and as such the bank is running on a singular controller which is a single point of failure for the entire Wi-Fi network.This necessitates the need for procurement process | Support throught the RFP process | In-Progress |  |  |  | High | Doreen Makutwa
8 | Duncan Situma | 1 | WI-FI 6 IMPLEMENTATION | Corebanking Migration Project. Mapping , Documenting the service,Specification Documentation ,Testing developed service . Supporting Peripheral CR Documentation. Roadmaps for out of Box Solutions | RoadMaps , Service Mapping , Testing and validation | In-Progress |  |  | Currently supporting development of Peripheral systems | High
|  |  | KB CBI | Design the Integration Solution for KB ATMS for Transaction processing and Account management | Solution Design | Completed
|  |  | KB ATM Integration | Enhance solution design for the branch instant issuance solution | Solution Design | Completed
|  | 2 | Branch Instant Issuance | Design a portal for onboarding of Money Market Fund (MMF) customers, allowing them to invest, withdraw funds, and compute investment interest while empowering portfolio managers to efficiently manage investments and generate reports. By digitizing these processes, the system aims to enhance customer experience, streamline operations, and ultimately drive increased bank deposits and profitability | Solution Design + Dev Support | Completed |  |  | Solution Currently under Development | High
|  | 3 | CISL | Design a n online bid bond platform , both customer facing and bank user facing to enable application and issuance of Guarantees | Solution Design | Completed |  |  | Solution in production | High
|  | 2 | Online Bid Bond MVP1 | Design an e-credit platform for serving non customers. | Solution Design | In-Progress |  |  | Updating solution after review with stakeholders
|  | 3 | KB Kopa Smart | Design the Transition architecture for The Elma platform capturing the different components , controls and integrations | Solution Design | Completed
|  | 4 | KB Elma | Design a n online bid bond platform , both customer facing and bank user facing to enable application and issuance of Guarantees | Solution Design | In-Progress |  |  | Requirements under Review Before Solutioning | High
|  | 5 | Online Bid Bond MVP2 | Design an e-credit engine | solution design | In-Progress |  |  | Technical alignment ongoing
9 | Abell Wandili | 1 | Co-op Foundation: University Module | Development of a university module of the Co-op Bank Foundation Management System, to manage the university scholarship program | Solution Design | Completed |  |  | Solution design completed and sent to developer | Medium | Regina Nzomo
|  | 5 | Co-op Soko Enhancements CR(25/005) | Project for enhancements for the Co-op Soko system | Amendment of the Get Account Details service to accomodate Loan Product Codes used in Mkulima Package | Completed | In-Progress | Completed | The service was deployed in SIT, testing was successful | Medium | Dorine Makutwa
|  | 6 | Co-op Soko Enhancements CR(25/005) | Project for enhancements for the Co-op Soko system | Solution design for proposed enhancements on the Buyers Module on Co-op Soko System - (Buyer Organization Sales Process Flow) | Completed | In-Progress |  | Solution Design complete. | Medium | Dorine Makutwa
|  | 2 | Co-op Soko Enhancements CR(25/005) | Co-op Soko Integration to Finacle to fetch updated loan products details | Provide a secure architecture that allows Co-op Soko get updated loan product details from Finacle | In-Progress |  |  | The Solution Design in progress | Medium | Dorine Makutwa |  |  | The script required for the service creation is still being optimized by DSG
|  | 8 | Co-op Soko Enhancements CR(25/005) | Co-op Soko Mkulima Package - Loan Disbursement | Amendment of the Loan Disbursement process and service from Trade Finance loan limit accounts to non-check off accounts | Completed | Completed | In-Progress | Solution Design Complete. | High | Dorine Makutwa
|  | 3 | Amendments on Agent Portal | Enhancement on the Agent Portal aimed at improving product offering and user experience | Solution Design | Completed |  |  | Solution Design completed and sent for review on 3-12-2025, with feedback pending on support from ICT Security on support to review the WAF rules | Medium | Angella Obiero |  |  | Request for resource from ICT Security to assist with WAF rules configurations
|  | 9 | Centralized Digital Folder for Salary Payment and Recovery File Exchange | Develop a secure Centralized Digital Folder for Salary Payment and Recovery File Exchange between the Bank internal users and External users for salary processing and payment | Solution Design | Completed |  |  | Solution Design Completed and sent for review by stakeholders | High | Kennedy Mutuku
|  | 10 | Pre-Personalized Student Prepaid Cards | Solution a streamlined process that allows customers(students) to receive a pre-printed, pre-encoded payment card instantly at branch locations or school outlets. This card will be unassigned to any customer until activation, when assigned to customers at the point of onboarding. | Solution Design | On-Hold |  |  | Project was halted after high risk exposure to the bank based on the proposed process flow | High | Faith Atoiti
|  | 7 | Processing of TSC Salaries on CBX | Amendment of the Solution Design Document for Processing of TSC Salaries on CBX | Solution Design amendment | Completed |  |  | Solution Design was completed and is under review by stakeholders and the developer | High | Elias Ronoh
10 | Joram Njagi
|  | 3 | CR - AUTOMATION OF IPF CANCELLATION AND NOTIFICATION PROCESS FOR BOTH IPFLN AND IPFLC | Automation of Insurance Premium Financing (IPF) cancellation and notification processes to facilitate the return of unutilized premiums to the bank upon customer default. | Solution Design | In-Progress |  |  | Cr Review with Remedial Team to update Business area concerns. | High | Amina Said
|  | 4 | DSL SYSTEM DEVELOPMENT | A compensation System design to to process and transfer the shares from DSL share accounts to Kingdom Securities Limited (KSL). | Solution Design | In-Progress |  |  | Database Access request and data sitting review. | High | DORINE ATEMI MAKUTWA
|  | 5 | Role Matrix Governance Framework and Centralized Repository Implementation | user access management across multiple systems for maintaining operational efficiency, regulatory compliance, and safeguarding the Bank’s sensitive information.
|  | 3 |  | Development of a centralized RFQ portal to digitize and streamline forex rate negotiations between customers, branch staff, and treasury dealers. The solution integrates with core banking (Finacle) and digital channels (CBX, RBX, MCo-opCash) to ensure efficiency, compliance, and real-time deal traceability | End to end solution Design | In-Progress |  |  | Studied the BRD and created a high level diagram of the solution. | Medium
11 | Faith N. Oling'a | 1 | Debit/credit alerts - Kingdom Bank | Capturing KB alerts that will be sent to customers who have subscribed.A notification is sent informing a customer of money debited from or credited to their account. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 2 | Alert for all Finacle loans dibursed | Customers receiving a Finacle disbursement for the Business and Personal loan to be charged an alert notification | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 3 | Alerts for Accounts Not Funded | An Account Not Funded Alert is a notification indicating that an account lacks sufficient funds to complete a transaction or meet requirements. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 4 | Unclaimed DD alerts | An UNCLAIMED_DD Alert is a notification indicating that a demand draft (DD) issued to a customer has not been claimed within the stipulated period. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 5 | Dormant Accounts alert | A notification sent to all customer whose account is about to go dormant due to inactivity 6Months | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 6 | Account Closure alert | A notification sent to inform a customer or system that a bank account has been closed, either by request or due to policy. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 7 | RTGS alert | An alert sent to the customer when money is transferred through RTGS, showing the amount, account, and transaction details. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 8 | SWIFT Incoming alert | An alert sent to the customer when funds are received through a SWIFT transfer, showing the amount, sender, and transaction details. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 9 | SWIFT Outgoing alert | An alert sent to the customer when funds are sent through a SWIFT transfer, showing the amount, beneficiary, and transaction details. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 10 | Standing Order Creation alert | A notification to all customers who have a standing order telling them that the SO has been processed | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 11 | Standing Order Amendment Alert | A notification triggered when changes are made to a standing order (SO) in the system. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 12 | Account Opening alert | A notification is sent confirming the successful creation of a new customer account. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 13 | Uncollected cheque books alert | A notification is sent to all customers with uncollected cheque books 30 days after production | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 14 | Cheque book pickup alert | A notification is sent informing a customer that their cheque book is ready for collection from the bank. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 15 | Unpaid cheque alert | Customers are notified of their unpaid cheques immediately it is noted they are upaid for various reasons. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 16 | Standing Instruction Creation Alert | A notification is sent confirming the successful setup of a new standing instruction (SI) in the system. | Solution Design | Completed |  |  | Solution design completed and sent to developer | High | Eldah Nyabiage
|  | 17 | Safe Custody alert | An alert is sent for payment on safe custody renewal | Solution Design | In-Progress |  |  | Solution design ongoing | High | Eldah Nyabiage
|  | 18 | Collateral Insurance Due alert | A notification is sent indicating that the insurance cover for pledged collateral is due for renewal or payment. | Solution Design | In-Progress |  |  | Solution design ongoing | High | Eldah Nyabiage
|  | 19 | Account Document Missing alert | A notification is sent indicating that required documents for a customer’s account are incomplete or not submitted. | Solution Design | In-Progress |  |  | Solution design ongoing | High | Eldah Nyabiage
|  | 20 | Loan due date alerts sent 7 days, 3 days, 1 day before due date and on due date | Alert is sent to customers/staff with upcoming loan instalments for all conventional loans within the bank | Solution Design and providing the data to be staged on Finacle | In-Progress |  |  | Data to be staged on Finacle for solution design to begin | High | Eldah Nyabiage
|  | 21 | Loan Arrears Reminder for overdue loans sent after 1,3,7,14,21,30,180 and 365 days | An alert sent to customers whose loan accounts are overdue, notifying them of the arrears and stressing urgent repayment to avoid further action. | Solution Design and providing the data to be staged on Finacle | In-Progress |  |  | Data to be staged on Finacle for solution design to begin | High | Eldah Nyabiage
|  | 22 | Loans CRB prelisting after 60 and 90 days | An alert sent to customers whose loan accounts are overdue, reminding them of the outstanding amount and telling them that they'll be listed on CRB. | Solution Design and providing the data to be staged on Finacle | In-Progress |  |  | Data to be staged on Finacle for solution design to begin | High | Eldah Nyabiage
|  | 23 | RFQ Portal | Working on the request and response mapping for customer inquiry and account inquiry. Service documentations will be created on the same and sent to developers. | Service Documentation | Completed |  |  | Met up with BI team and requested that all reports originate from a central point instead of being provisioned from different systems | Medium | Eldah Nyabiage
|  | 24 | Branch Reports | A system should be built to ensure that branch reports are generated from an application instead of being printed so that we can cut down on cost. | Solution Design | In-Progress |  |  | Met up with BI team and requested that all reports originate from a central point instead of being provisioned from different systems | Medium | Rosemary Nduta
|  | 25 | FX Rates File Converter | An application used to convert the file with rates generated from external systems in excel formal into a txt format that is compatible with Finacle for rate upload. | Solution Design, Server specification | Completed | In-Progress |  | Completed solution design and submitted to developer for review. Received KB LDAP details and provided the same to the developer for AD configuration. Gave server specifications to KB for provisioning of the same so that the developer could access the DB, create a user and test. | Medium | Eldah Nyabiage
12 | Ann Madigo | 1 | East African Tea Trade Association (EATTA) | This project seeks to modernize the tea auction, warehousing, and settlement ecosystem by resolving current inefficiencies and positioning the Bank as the leading financial partner in the sector | BRD Review | Re-assigned |  |  | Reviewed BRD and contributed to how the new functionality may be incorporated into Co-op Soko as a Change Request |  | Clara Watuha
|  | 2 | Till Solution Enhancement | This Change Request (CR) proposes an enhancement to extend DLL compatibility to additional programming languages and environments, ensuring broader integration capability and improved flexibility for merchants operating on diverse RMS platforms. | Solution Design | Completed |  |  | Met with vendors who have proposed a solution for Merchants who are on ODOO ERP which is Python based. We have requested that they expand their scope to include all existing ERPs for 2 new customers that the bank is onboarding. |  | Clara Watuha | 21/10/2025
|  | 3 | CRB APIs Integration | This Change Request proposes an automated credit information sharing solution integrating Metropol and TransUnion CRB APIs with Finacle, Omni, and CMS systems. Replace manual 3-hour daily process with real-time API-based transmission. | Solution Design | In-Progress |  |  | Solution Design Document is complete |  | Marystella Obutsula
|  | 4 | Jumbo Junior Account Opening - Birth Certificate OCR Enhancements | 1. Model Upgrade | Solution Design | Completed | Completed | In-Progress | Solution is in Production
2. Token Limit Increased
3. Temperature Optimization
4. Image Compression
5. Image Enhancement
6. Content Order Optimization
7. Enhanced Prompt Engineering
8. Quality Control Improvements
9. Retry mechanism
|  | 5 | ​​APP.BS.Card.Replacement.1.0​ | This service will be used by channel applications to replace an existing card with a new card. The service allows for card replacement scenarios including lost, stolen, damaged cards, or upgrades to new BINs. | Service Documentation | Completed | Completed
|  | 6 | VISA Stop Payment Service Test Cases | VISA Stop Payment Service Test Cases | Test Cases | Completed
|  | 7 | AI INTEGRATION ROADMAP | A roadmap for embedding Artificial Intelligence in Co-Operative Bank. | Solution Design | In-Progress
|  | 8 | Validation of B2C Transactions via Hakikisha API | The Hakikisha API provides real-time validation of M-Pesa wallet holder names before fund transfers, significantly reducing erroneous transactions and improving customer experience. | Solution Design | Completed
|  | 9 | APP.BS.Customer.RetailContactCIfConversion.Post.1.0 | Contact CIF to Retail CIF Service. When agents are onboarded at Co-operative Bank, they are initially assigned a Contact CIF, which has limited functionality. To enable these agents to access digital banking channels and perform full banking operations, they need to be converted to Retail CIF status. | Service Design & Documentation | Completed | In-Progress
|  | 10 | 360 Admin Portal | The solution provides frontline teams (Contact Centre, Branch Support) with a unified, real-time view of customer information, transactions, and activities across all digital channels. | Solution Design | Completed
|  | 11 | QR Seamless Credentials Sharing | Eliminate password entry on web portal entirely. Users authenticate by scanning a QR code with their mobile banking app, which is already authenticated. Complete phishing immunity. | Solution Design | Completed
|  | 12 | Deep Links Setup |  | Solution Design | Pending
|  | 13 | Progressive Onboarding | The solution addresses high customer abandonment rates caused by the current all-or-nothing validation approach by implementing a two-phase progressive onboarding system. | Solution Design | Completed
|  | 14 | APP.BS.BeginningOfDayValidation.Post.1.0 | The service validates whether a given date matches the current Finacle Core Banking System date, enabling channel applications to determine if they can proceed with date-sensitive transactions and operations. | Service Design & Documentation | Completed
|  | 15 | APP.BS.Account.SignaturesQuery.Post.1.0 | This service provides Account Signatures Query functionality for the Finacle Core Banking System. The primary purpose is to support duplicate checking during account opening and customer onboarding processes. | Service Design & Documentation | Completed
|  | 16 | AI Risk Assessment | This document provides comprehensive responses to the AI Governance Questionnaire for Co-operative Bank of Kenya's operations |  | Pending
|  | 17 | STATUTORY PAYMENTS – SHIF, KARGOPAY AND NSSF | This function enables a retail customer to make payments to SHIF, NSSF and Kargopay directly from the Omni Channel. | Solution Design | Completed
13 | Simon Thuku | 1 | Loan Track Change Request | Change Request Titles: 1. Automation of E-Credit and Overdraft Account Listing in Loan Track for Loan Appraisal | Solution Design | Completed | Completed | In-Progress | - Solution Design Document - Done |  | Brigid Fernandes
|  |  |  | 2. Addition of "Signature Mismatch" as a Decline Reason in Loan Track |  |  |  |  | - Development - In progres
|  | 2 | DSL System Upgrade | Mordernize the current DSL system | Solution Design | In-Progress |  |  | - BRD review - done. |  | Dorine Makutwa
- Solution Design Document - done
- Requested for the current DSL DB access - done
- Data Architecture - in progress
|  | 3 | Enhancement of C2B Transactions Reversal Process on BPMS | Improvements of MPESA reversals and B2C payouts for partial reversals | Solution Design | In-Progress |  |  | - BRD Review - done |  | Eva Gitau
- No new service as earlier communicated. Reuse the existing B2C SOA services
- Solution Design - in progress
- The BA is not available to address the remaining open points
|  | 4 | IVR Enhancement & IVR Mpesa reversal project | MPESA reversals on IVR | Solution Design | In-Progress |  |  | - Solution Design - in progress |  | Eric Mbatia
- A walkthrough with the IVR team on 2025/12/08
|  | 5 | Loan Track validations | Implementation of Validation Rules in Loan Track System | Solution Design | Completed |  |  | - CR review - done |  | Brigid Fernandes
- System walkthrough - done
- Solution Design - done
|  | 6 | KPC IPO INTEGRATION | Integration with Pesalink, Swift/RTGS and EFT | Solution Design | Completed | Completed | Completed |  |  | Clara Watuha
6 | Michael Malala | [8 empty] | Medium
|  | 1 | Ecredit top up across tenure | Allow top up of loan across all the tenures | Solution Design | Completed |  |  |  | Medium
|  | 2 | SWIFT Payment Pre-validation API | Integration of SWIFT’s pre-validation API to validate beneficiary details (e.g., IBAN, BIC, account format) before sending international payments. It helps reduce failed transactions and associated costs | Solution Design pending | Completed |  |  |  | Medium | Kamonye
|  | 3 | Swift GPI Tracking implementation in OMNI | Integration of SWIFT Global Payments Innovation (GPI) tracking within the OMNI platform to provide end-to-end payment traceability, transparency, and real-time updates for cross-border transactions. | Solution Design pending | Completed |  |  |  | Medium | Kamonye
|  |  | cooptil overdraft | extend overdraft feature to Coop Kwa Jirani | Solution Design | Completed
|  | 4 | KPLC Prepaid Token Purchase on POS | Token Purchase from POS device | Solution Design | Completed |  |  |  | Medium | Maru
|  | 1 | T-Bill and T-bonds on CBX via B2B | Facilitates the purchase and management of Treasury Bills and Bonds through the CBX platform using B2B integration, allowing institutional clients to interact seamlessly with treasury instruments via APIs or system-to-system connections. | Solution Design pending | On-Hold |  |  |  | Medium | Maru
|  |  | Pesalink update | Update pesalink to be in line with pac 08 | service design | Completed
|  |  | Card Renewal Journey | a new card renewjorney for our customers to | solution design | Completed
|  | 2 | Omni Channel account onboarding optimization | Relook at the onboarding journey and reduce the fields | solution design | In-Progress
|  |  | cooptill multiple tills | Allow access of admin to view all thier cooptills from single login | solution design | Completed
|  |  | coop kwa jirani float purcahse | Update of the coop kwa jirani overdraft for agencies | solution design | Completed
|  |  | secured business plus loan across tenure | Availing the collateral linked loan for all tenures | solution design | Completed
|  |  | Digital lock wallet | Update digital lock service to restrict external wallet deposit | solution design | Completed
|  | 3 | One login for multiple Co-op Tills | Allow coptill admin login in multiple tills from same session | solution design | Completed
|  | 4 | alerts engine base scale up | new alerts that cusomers will subscribe to via omni or common admin | Solution Design | Completed
|  | 5 | incomplete Paybill transactions | review paybill intergration to determine cause of incomplete paybill transactions | Solution document | In-Progress
|  |  | Alerts Base Scale Up | Solution Design to facilitate upload of document at common admin for alerts to users | Solution document | Completed
|  |  | Sacco User Audit trail | Track sacco members user trail while using the web app extended to their conusmenrs | Solution document | Completed
|  |  | TMS-RBX | solution design for RBX and TMS | Solution design | Completed
|  |  | Cardless Withdrawal reversal | design new solution document to accomodate cardless withdrawal | solution document | Completed
|  |  | Cooptill aitime Purchase | Cooptill airtme purchase to allow agents purchase airtime | solution document | Completed
|  | 6 | Super App POC | Development of a prototype version of a Super App that consolidates multiple digital services—such as payments, banking, investments, mobile top-ups, and lifestyle features—into a single platform. | Solution Design Proof of concept | On-Hold |  |  |  | High
|  | 7 | CBX PARTIALLY POSTED FILES | allow overdraft of sacco suspense account | Solution Design | Completed |  |  |  | high
|  |  | MONEYGRAM ON MCOOPCASH | Money gram service intergattion to omni channel to allow customers perfom cross border tansaction via omni channel | Solution Design | Completed |  |  |  | high | Shirleen
|  | 8 | CALL DEPOSIT ACCOUNT OPENING PROCESS ON BPMS | Process to digitalize the Call Deposit account opening | solution Design | Completed |  |  |  | medium
process using the Business Process Management System (BPMS) and details its
integration with Finacle for automated account opening and funds transfer.
|  | 8 | CO-OP DUKA Logistic Module | Internal dispatch of co-op duka products | solution design | Completed |  |  |  | medium
|  |  | E Loan Deceased Account | a job/process in place from eloans that updates a custom Finacle table (customcopke.eloans) with data of all loans in ‘Active’ or ‘Default’ status. | Solution Design | Completed |  |  |  | medium
|  |  | Account balance on OMNI API solution design | omni channels to retrieve account balance from core banking system via SOA by passing the internal components of the vendor to enhance User experience | Solution design | Completed
|  |  | security questions on OMNI API solution | specification for a web service that will be used by omni channels to retrieve security questions from Df database via omni api | Solution design | Completed
|  |  | Wallet as a service - SOA services | to enhance the existing wallet engine to create a platform that drives increased utilization and profitability by extending wallet services to non-Co-op Bank customers and wallet-only MCo-op Cash users |  | Completed
|  |  | Wallet as a service - Open Banking | Document wallet as a service API |  | Completed
|  |  | Alert Base scale up | "Pick" logic for alerts in the staging table is to enable multiple downstream channels to concurrently consume alerts from the queue without conflict or data loss | Review the Logic | Completed
|  |  | Swift advice soa service | web service that will be used by CBX clients to download swift response messages after successful transaction | Solution Design | Completed
|  |  | pay to card from mpesa | enables customers to deposit or pay to their credit and debit cards directly from M-PESA within the OMNI platform, accessible via YEA and Mco-opCash APP, WEB, and USSD. | Solution Design | Completed
|  |  | KPLC prepaid on co-optill app | will enable customers not on the OMNI channel or non-coop account holders to buy KPLC prepaid tokens from our co-optill merchants. | Solution Design | Completed
|  |  | Alerts Eloans | mandatory alerts for all loan disbursed | Solution Design | In-Progress
|  |  | Continous Loan repayment | enhance the eloans engine to facilitate contionus hunting of overdue loans | Solution Design | Completed
|  |  | CISL-OMNI Intergration | CISL intergration to omni channel | Solution Design | Completed
|  |  | Credit Scoring | Intergrate perfios tool to facilitate document extraction to be used in enriching credit scoring | Solution Design | In-Progress
Sacco Keycloak Intergration
|  |  | Budget analysis tool | A budget analysis tool for omni | Solution Design | In-Progress
|  |  | western union sub agents | Intergrate Western Union Agent Host to facilitate western union agent transactions | Solution Design | Completed
|  |  | CBX -PCS INTERGRATION | CBX -PCS intergration to allow self service for fund managers to initiate custody transactions | Solution Design | Completed
|  |  | Sacco Kenya Police | provide a comprehensive overview of the integration of the Kenya Police SACCO into our SACCO channel, focusing on the key technical components required to support the initiative. | Solution Design | Completed
| Kelvin maxwell Murithi |  | MTN south sudan integration | This project aims to intergrate south sudan with MTN which is an ISP from there to enable USSD transaction with more potential customer base to widen their market base | MTN B2C AND C2B INTEGRATION | In-Progress |  |  | COBSS to close integration with MTN on B2B escrow integration first then emback on B2C and C2B bethwell to advise once done | medium
|  |  | MTN REMMITANCE INTEGRATION | integration to a remmitance vendor for the south sudan account MTO | Remmitance solution sourcing for vendor | In-Progress |  |  | vendor selection has reached the final stages VASMOBILE FINTELCO was selected and now proceedign to the BPMS approval stage financials also done | medium
|  | 1 | PAYTOFOSA integration | to integrate the TSC to the various saccos and automate salary payment flow | TSC salary payment to SACCOS | Completed |  |  | in development with SDU team | high
|  | 2 | CMS (card management system) project | this project aims to enable customers to view thier bonus points from the comfort of thier phones and other OMNI channels | solution design in draft | Completed |  |  | pushed to digital factory for development | medium
|  | 3 | cooperative bank foundation program | This project aims to onbord students from both primary and high school to both secondary and university | solution design done and is in development | Completed |  |  | in development | HIGH
|  | 4 | Overview of Enhancement of KYC and risk profiling for client onboarding in IPEN. | This change request proposes enhancements to the current Know Your Customer (KYC) process and risk profiling during client onboarding in the IPEN system. The goal is to address existing gaps by: § Improving the identification of Politically Exposed Persons (PEPs), § Enhancing client occupation classifications, § Streamlining mandatory fields required for both individual and corporate clients. § Improving data accuracy, and reducing potential risks associated with inaccurate client profiling. | solution design to enhance KYC profiling | Completed |  |  | meeting set for monday with vendor pensoft meeting to review the quote and next steps on API integrations to happen | Medium | Brigid fernandez
|  | 7 | Asset finance project | Asset Financing is a self-securing loan product for financing of moveable assets such as laptops, computers, printers, saloon cars, pickups, tractors, prime movers, school buses, generators and even medical equipment | solution design done | Completed |  |  | in development with SDU team | HIGH
Customers who wish to apply for an Asset Finance facility must do so physically at the branches through Business Bankers, Personal Bankers and other sales teams. Customers must provide hard copy KYC documents which are vetted by the branch sales staff, applications forms filled in and sent via Loan track/BPMS to CMD for analysis and processing.
|  |  | cooperative bank student foundation module secondary and unversity enhancement | this project aims to enrich the secondary and university modules with updates meant to enable business capture and achieve thier goals | solution design done | Completed |  |  | Sits ongoing with bug fixing being done with SDU team preparing for production on the secondary module | high
|  |  | coopfoundation university module build | Co-op bank foundation has a scholarship program for students in secondary schools and universities. The foundation has an existing system for the secondary school scholarship program. The foundation is currently processing university fees manually where a program officer, receives applications, prepares spread sheets and payment. This presents the risk of double payment alongside clerical related errors and inefficiencies. The foundation has also recently doubled the intake of university students from 28 students to 56 students per year. | solution design in draft | Re-assigned |  |  |  | Medium | Regina nzomo
The new government funding model complicates the situation where unlike before, students are charged fees based on the courses they are pursuing and family background.
Because of the unique characteristics brought about by the Government’s funding model and the increase in the number of active beneficiaries at any given time, there is need to develop a system that will enable the Foundation to manage the program efficiently. This will also ensure compliance, proper internal controls and adherence to other core activities of the program, i.e. community service, internships and performance monitoring within the program.
|  |  | CRB INTEGRATION API | the aim of this project is to integrate transunion and metropol into the banks system for ease of verification and to reduce time on individual screening | solution design in draft | In-Progress |  |  | BCM to sign contract with vendor and get test credentials for the API environment to be shared by vendor once contract is signed and approved | medium
|  |  | Bancassurance project | This project is about automation of the motorvehicle car insurance cover VIA DMVIC and AKI insurance | Solution design done | Completed |  |  | solution design done and service has been developed and tested | Medium
|  |  | coop bank foundation secondary module/university | this project aims to do enhancements on both the secondary and university module for the co-opbank foundation program | solution design done secondary module | Completed |  |  | develoment ongoing on the secondary module | High
|  | 1 | Trade Finance | The AARO Financial Consolidation Tool is a software solution used primarily by large and mid-sized organizations to automate, streamline, and standardize the process of consolidating financial data from multiple subsidiaries, departments, or entities. | Solution design | Completed |  |  | KE done . Ongoing process for Alerts , SS and KB to be scoped | High | Joyse ndumbi
|  | 2 | AARO Financial consolidation tool | The process of overdrawing an account to perform a cash reversal involves temporarily allowing a customer’s account to go into a negative balance (i.e., overdrawn) in order to reverse a previously posted cash transaction, such as an incorrect credit or debit. This is typically done when there are insufficient funds to offset the reversal naturally | Solution design | Completed |  |  |  | Medium
|  | 3 | Reversal | A change request to include mandatory fields involves modifying an existing system or process to enforce the input of specific data elements before a transaction or record can be successfully saved or submitted. This ensures data completeness, consistency, and compliance with business or regulatory requirements. The change typically specifies which fields are to be marked as mandatory | Mandatory Fields | Completed |  |  |  | Medium
|  | 4 | Mandatory Fields Instant cash | This project aims to onbord students from both high primary and high school to both secondary and university | Solution design done | Completed |  |  |  | Medium
|  | 7 | DSS | Direct Settlement system | Solutioning | In-Progress |  |  | DSS KRA intergrations solution , Manual grower and service provider settlement solution. Loan Recovery on manual settlement. Multiple Vehicle and Driver on collection details, Catalogue and Auction file validation solution. | High
|  | 6 | CROPS Data Cleanup Process -Arrears Recovery | CROPS Data Cleanup Process -Arrears Recovery | Mapping | Completed |  |  |  | High
|  | 8 | QR code Validator | A QR Validator is a tool or system used to verify the authenticity or validity of a QR code. It scans the QR code, extracts the embedded data (such as a URL, ID, or token), and checks it against a trusted source (like a database or API) to confirm whether the code is valid, unexpired, and authorized for use. QR Validators are commonly used in event check-ins, secure logins, digital tickets, or product verification. | Solution document | Completed |  |  | Currently under SIT testing | Medium
|  | 8 | Echecker enhancements | Fetching missing data, ability to reveiw skipped transactions, | Solutioning | Completed |  |  | Solution Reveiw by Dev team | High
|  | 9 | Asset Fiance Intergrations | BPMS FINACLE and LOAN TRACK intergtations | Solution document | Completed |  |  | Intergration pending finance input | High
|  | 10 | SHIF & B2B POS Enhancements | STK push intergration on POS , ECR Merchants and Agents | Solution document | Pending |  |  | Pending STK updates for single debit multiple credits | Medium | Clara Watuha
|  | 11 | Trade Finance | Post go live Alerts solutioning | Solution document | In-Progress |  |  | Pending Finacle updates on staged data | High | Clara Watuha
|  | 7 | AUTOMATE FINACLE PLSP ARREARS RECOVERY MENU | Enhance reporting on items consolidation. | Solution | Completed |  |  | Done | High
|  | 8 | Echecker enhancements | Inability to verify skipped transactions | Solution | Completed |  |  | Pending BI input on the optimization | Medium
Inability to generate reports by account scheme
Inability to display final comments on missing transactions
Inability to show payee data for in-house cheque transactions
Inability to display all components of multi-loop transactions. There are these items required by business on echcker, how does it sit, is it one monolithic system ama inakaa aje, just a summary nijue how to approach this.
|  | 12 | Mpesa Trust | Error on withdrawals to other Bank accounts via PesaLink. | Solutioning | In-Progress |  |  | Pending account Overdraft whitelisting | High
|  | 13 | Loan Track | Update allowing TSC employee for for -14 days top up | Solution design | Completed |  |  | Solution Reveiw by Dev team | Medium
|  | 14 | KB motioring and reconciliation | Recon reports generation | Solution design |  |  |  | Problem statement review | High